## RISK REGISTER
[INSERT NAME] RISK REGISTER
Description |  |  |  |  | Measures | [5 empty] | Status and review
Risk ID Code | Risk | Risk Description | Risk Owner | Strategic Plan Theme | Gross risk (pre-controls) |  | Control Measures Employed | Net Risk (post-controls) |  | Comments / Further Actions Required / Contingency Plan - including deadline dates | Last Review Date | Next Review Date | Current Status | Overall indicator
[5 empty] | Likelihood (1,2,3,4,5) | Impact (1,2,3,4,5) |  | Likelihood (1,2,3,4,5) | Impact (1,2,3,4,5)
1.1 | Technical | Lack of knowledge on the selected topic | Abit Mahato | N/A | 2 | 4 | Online learning | 4 | 5 | Asking help with friends and tutors | 2022-02-01 | 2022-02-09 | New | NRed | 20 | Red
1.2 | Technical | Powe cuts | Abit Mahato | N/A | 2 | 3 | Backup for laptop and routers | 3 | 2 | Continuing with backup | 2022-02-01 | 2022-02-05 | Reducing | ↓Green | 6 | Green
1.3 | Technical | Slow internet connection | Abit Mahato | N/A | 2 | 3 | Mobile data | 2 | 2 | Managing or asking for better connection with ISP | 2022-02-01 | 2022-02-05 | Imminent | !Green | 4 | Green
1.4 | Technical | Issues with working devices | Abit Mahato | N/A | 3 | 2 | Taking good care of working device | 3 | 2 | Continuing on same device | 2022-02-01 | 2022-02-15 | New | NGreen | 6 | Green
2.1 | Project | Not completing the project on time | Abit Mahato | N/A | 2 | 2 | Working hard for project | 4 | 2 | Regularly working on project | 2022-02-01 | 2022-02-25 | New | NGreen | 8 | Green
2.2 | Health | Health issueses due to ongoing Covid vairants | Abit Mahato | N/A | 3 | 3 | Taking safety precautions | 4 | 2 | Not going out of house unless its necessary | 2022-02-01 | 2022-02-05 | Increasing | ↑Green | 8 | Green
2.3 | Orginazation | Lack of co-ordination with supervisor | Abit Mahato | N/A | 2 | 2 | Attending meeting with supervisor on allocated time. | 3 | 2 | Always in touch with supervisor | 2022-02-01 | 2022-02-15 | New |  | 6 | Green
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0
0

## RISK PROFILE
[INSERT NAME] RISK REGISTER
Status of risks |  | Current Total
New | N | 4
Unchanged | ↔ | 0
Increasing | ↑ | 1
Reducing | ↓ | 1
Imminent | ! | 1
Closed | x | 0
Net risk score |  | Current Total
Red |  | 1
Amber |  | 0
Green |  | 6

## CLOSED RISKS
Description |  |  |  |  | Measures | [5 empty] | Status and review
Risk ID Code | Risk | Risk Description | Risk Owner | Strategic Plan Theme | Gross risk (pre-controls) |  | Control Measures Employed | Net Risk (post-controls) |  | Comments / Further Actions Required / Contingency Plan - including deadline dates | Last Review Date | Next Review Date | Current Status | Overall indicator
[5 empty] | Likelihood (1,2,3,4,5) | Impact (1,2,3,4,5) |  | Likelihood (1,2,3,4,5) | Impact (1,2,3,4,5)
[13 empty] | Closed | X

## Guidance Notes
Risk Register Scoring Guidance Notes | [7 empty] | V③
Likelihood (1, 2, 3, 4, 5)
Ø Identify the likelihood of the gross risk using the following table (taken from the Risk Management Policy).
Ø Likelihood – what is the likelihood of materially failing to achieve the objective / outcome?
Table 1 Risk Likelihood Framework:
LIKELIHOOD | SCORE | CRITERIA | DESCRIPTION
Very High | 5 | > 75% | Almost certainly will occur
High | 4 | 51 – 75% | More likely to occur than not
Medium | 3 | 26 – 50% | Fairly likely to occur
Low | 2 | 6 – 25% | Unlikely to occur
Very Low | 1 | 0 – 5% | Extremely unlikely or virtually impossible
Impact (1, 2, 3, 4, 5)
Ø Identify the impact of the gross risk using the following table (taken from the Risk Management Policy).
Ø Impact – What is the impact on the University of materially failing to achieve the objective / outcome?
Table 2 Risk Impact Framework:
| CORPORATE |  |  |  | FACULTY/SERVICE |  | PROJECT
5: CATASTROPHIC | • Would pose a serious threat to the University’s survival • Would prevent the achievement of corporate objectives • Would have very serious financial consequences that may not be manageable with existing university resources • Would necessitate very significant changes to the University’s structure, priorities, and systems/procedures • Sustained national media coverage: perceived total loss of public confidence |  |  |  | • Would pose a serious threat to the faculty’s/service’s survival • Would prevent the achievement of faculty/service objectives • Would have very serious financial consequences that may not be manageable with existing faculty/service resources • Would necessitate very significant changes to the faculty’s/service’s structure, priorities, and operational delivery • Would have a major impact at University level |  | • Would pose a serious threat to the project’s survival • Would prevent the achievement of project objectives • Would have very serious financial consequences that may not be manageable with existing project resources • Would necessitate very significant changes to the project plan, intended outcomes, and operational delivery • Would have a major impact at faculty/service level and/or a moderate impact at University level
4: MAJOR | • Would seriously hinder the achievement of corporate objectives • Would have serious financial consequences that may require significant reallocation of university resources • Would necessitate some changes to the University’s structure and/or priorities • Would necessitate significant changes to University systems/procedures • Sustained local and/or some national media coverage: longer-term perception of not meeting public expectations |  |  |  | • Would seriously hinder the achievement of faculty/service objectives • Would have serious financial consequences that may require significant reallocation of faculty/service resources • Would necessitate some changes to the faculty’s/service’s structure and/or priorities • Would necessitate significant changes to operational delivery in the faculty/service • Would have a moderate impact at University level |  | • Would seriously hinder the achievement of project objectives • Would have serious financial consequences that may require significant reallocation of project resources • Would necessitate some changes to the project plan and/or intended outcomes • Would necessitate significant changes to project delivery • Would have a moderate impact at faculty/service level and/or a minor impact at University level
3: MODERATE | • Would hinder the achievement of some corporate objectives • Would have financial consequences that could be managed by flexing existing budgets • May necessitate some changes to the University’s structure and/or priorities • Would necessitate some changes to University systems/procedures • Local media coverage: some short term perception of not fully meeting public expectations |  |  |  | • Would hinder the achievement of some faculty/service objectives • Would have financial consequences that could be managed by flexing existing faculty/service budget • May necessitate some changes to the faculty’s/service’s structure and/or priorities • Would necessitate some changes to operational delivery in the faculty/service • Would have a minor impact at University level |  | • Would hinder the achievement of some project objectives • Would have financial consequences that could be managed by flexing existing project budget • May necessitate some changes to the project plan and/or intended outcomes • Would necessitate some changes to project delivery • Would have a minor impact at faculty/service level and/or an insignificant impact at University level
2: MINOR | • Would hinder the achievement of some aspects of corporate objectives • Would have financial consequences that could be managed with existing budgets • May necessitate some changes to University systems/procedures • May give rise to questions about the extent to which public expectations are being met |  |  |  | • Would hinder the achievement of some aspects of faculty/service objectives • Would have financial consequences that could be managed with existing faculty/service budget • May necessitate some changes to operational delivery • Would have an insignificant impact at University level |  | • Would hinder the achievement of some aspects of project objectives • Would have financial consequences that could be managed with existing project budget • May necessitate some changes to project delivery • Would have an insignificant impact at faculty/service level
1:INSIGINFICIANT | • Would have only a marginal effect on the achievement of some aspects of corporate objectives • Would have only marginal financial consequences • Would be managed with existing systems/procedures • Little impact on public perceptions |  |  |  | • Would have only a marginal effect on the achievement of some aspects of faculty/service objectives • Would have only marginal financial consequences • Would be managed with existing systems/procedures |  | • Would have only a marginal effect on the achievement of some aspects of project objectives • Would have only marginal financial consequences • Would be managed with existing systems/procedures
Table 3 Risk ‘Response’ Matrix:
IMPACT | Catastrophic | Amber | Amber | Red | Red | Red
5
| Major | Green | Amber | Amber | Red | Red
4
| Moderate | Green | Green | Green | Amber | Amber
3
| Minor | Green | Green | Green | Green | Green
2
| Insignificant | Green | Green | Green | Green | Green
1
Net Risk Exposure (Impact / Likelihood) |  | Very Low | Low | Medium | High | Very High
|  | 1 | 2 | 3 | 4 | 5
LIKELIHOOD
Appetite Key Green = Within Appetite / Tolerate Orange = Outside Appetite / Don’t Tolerate / Take Action to Reduce Risks. Red = Outside Appetite, definitely don’t tolerate, consider stopping action / project to remove such high level of risk.

## Risk_Lookup (hidden)
Likelihood | Impact | ConcatenateScore | Risk Indicator
1 | 1 | 11 | Green
1 | 2 | 12 | Green
1 | 3 | 13 | Green
1 | 4 | 14 | Green
1 | 5 | 15 | Amber
2 | 1 | 21 | Green
2 | 2 | 22 | Green
2 | 3 | 23 | Green
2 | 4 | 24 | Amber
2 | 5 | 25 | Amber
3 | 1 | 31 | Green
3 | 2 | 32 | Green
3 | 3 | 33 | Green
3 | 4 | 34 | Amber
3 | 5 | 35 | Red
4 | 1 | 41 | Green
4 | 2 | 42 | Green
4 | 3 | 43 | Amber
4 | 4 | 44 | Red
4 | 5 | 45 | Red
5 | 1 | 51 | Green
5 | 2 | 52 | Green
5 | 3 | 53 | Amber
5 | 4 | 54 | Red
5 | 5 | 55 | Red